## Sheet1
Module	Task ID	Task Description	Duration	Week	Status
Login Module	1.1	Project environment setup (Git, Hosting, DB)	0.5 day	Week 1
	1.2	Build Login + JWT Session Management API	1 day
	1.3	Implement 2FA Email OTP (generate, send, verify, expiry)	1 day
	1.3a	Resend OTP feature	0.25 day
	1.4	React Login UI + 2FA screens + Validation/Error Handling	1 day
	1.5a	Forgot Password Request (Send reset link to email)	0.5 day
	1.5b	Reset Password Page (Token validation + new password)	0.5 day
	1.6	Unit testing & bug fixes for auth flow	0.5 day

Advisor Module	2.1	Advisor Dashboard UI (Greeting, Metrics, Charts, Sidebar)	1 day	Week 2
	2.2	Advisor → Client Table View (search, sort, paginate)	0.75 day
	2.3	API: Clients CRUD + Search + Filters	1 day
	2.4	Add/Edit Client Modal with Validation	0.5 day
	2.5	Email Modal with Rich Text Editor (Send text emails to clients)	0.25 day
	2.6	Client Summary View + Document Upload UI	0.75 day
	2.7	File Upload API + Secure Storage + Role-based access	0.5 day
	2.8	Complete Advisor Module Testing & Fixes	0.5 day

Admin + Client Modules	3.1a	Admin Settings UI (2FA toggle, password policy, timezone)	0.5 day	Week 3
	3.1b	Admin Theme Settings (Theme, Font Size/Type)	0.25 day
	3.2	Fact Finder Configurator (Dynamic Question Builder - checkbox, MCQ, input)	1 day
	3.3	Client Dashboard UI + Sidebar Navigation	0.5 day
	3.4a	Fact Finder Multi-Step Form (Personal Info, Assets, etc.)	0.5 day
	3.4b	Auto-Save Logic + Continue/Back Navigation + Progress Bar	0.5 day
	3.5	Load Dynamic Questions in Client View (Investor Profile logic)	0.5 day
	3.6	Income Tax Calculator (Form Inputs + Graphical Output)	0.75 day
	3.7	Final Testing	0.5 day
	3.8	Deployment	0.25 day